## Bulk Import
Report Date | Scope | Discipline (PM/CM/General) | Activity | Location | Sort Field | SAP # | Reference # | Plan Start | Plan Finish | Actual Start | Actual Finish | Planned Hours | Actual Hours | Status | Week | Remarks | ABC Indicator (A/B/C, optional)
2026-01-09 | Descon | PM | Overhaul PSV-101 (Size 0.5in 150# RF) | AR-AREA1 | X-A9902C | 401572541 | PTW-2201 | 2026-01-09 | 2026-02-09 | 2026-01-09 | 2026-02-09 | 8 | 8 | Completed | W1 | EXAMPLE ROW - delete before pasting your data | A
2026-01-09 | Descon | CM | Replace corroded flange gasket | AR-AREA2 | X-B1034D | 401572542 |  | 2026-01-09 | 2026-01-09 | 2026-01-09 |  | 4 | 2 | In Progress | W1 | EXAMPLE ROW - delete before pasting your data
2026-02-09 | Descon | General | Housekeeping - equipment area cleanup | AR-AREA3 | X-C2201F | 401572543 |  | 2026-02-09 | 2026-02-09 |  |  | 2 | 0 | Not Started | W1 | EXAMPLE ROW - delete before pasting your data

## How to use
HOW TO USE THIS TEMPLATE
1. Fill in your activities in the 'Bulk Import' sheet, one row per activity - keep the columns in this exact order.
2. Delete the three example rows (shaded/italic) before you paste your real data, or add your rows below them.
3. Dates: use DD/MM/YYYY (e.g. 01/09/2026).
4. Discipline: PM, CM, or General.
5. Status: Not Started, In Progress, Completed, or Rescheduled.
6. ABC Indicator: A, B, C, or leave blank if the activity is not a Safety Critical Equipment (SCE) item. Only Category A counts toward the SCE KPI.
7. Reference #, Remarks and ABC Indicator can be left blank if not applicable.
TO IMPORT INTO THE DASHBOARD:
- Select your filled-in rows in the 'Bulk Import' sheet (do not select the header row), copy them (Ctrl+C).
- In the dashboard, open 'Add / edit activities' and paste into the 'Bulk paste from Excel' box.
- Click 'Import pasted rows'.