## Instructions
Budget & Revenue Monitoring Dashboard
Track project budget consumption, revenue, and Earned Value (EVM) in one workbook.
How this workbook is organized
Setup | Enter your project name, total approved budget (BAC), total contract/expected revenue, and project dates. Everything else calculates from these.
Monthly Tracking | Enter ONE row per month: planned % complete, actual % complete, consumed budget (actual cost) for the month, and revenue invoiced/received for the month. All Earned Value metrics (PV, EV, AC, CV, SV, CPI, SPI) and profit figures calculate automatically.
Dashboard | Live KPI cards and charts pulled from Monthly Tracking - Budget vs Consumed vs Revenue, the EVM S-curve (PV/EV/AC), CPI & SPI trend, and cumulative profit. Nothing to edit here.
Color legend
Blue text on yellow fill | Cells you fill in (inputs).
Black text | Formulas - do not overwrite, they recalculate automatically.
Green text | Links pulling values from another sheet.
Key terms (Earned Value Management)
PV - Planned Value | Budgeted cost of work that SHOULD be done by now = Total Budget x Planned % Complete.
EV - Earned Value | Budgeted cost of work ACTUALLY done = Total Budget x Actual % Complete. This is your project's 'earned value'.
AC - Actual Cost | Money actually spent so far = Consumed Budget (cumulative).
CV - Cost Variance | EV - AC. Positive = under budget for the work completed. Negative = overspending.
SV - Schedule Variance | EV - PV. Positive = ahead of schedule. Negative = behind schedule.
CPI - Cost Performance Index | EV / AC. Above 1.00 = spending efficiently. Below 1.00 = over budget for work done.
SPI - Schedule Performance Index | EV / PV. Above 1.00 = ahead of schedule. Below 1.00 = behind schedule.
Revenue vs Consumed Budget | Revenue (invoiced/earned) minus Consumed Budget (actual cost) = Gross Profit for the project to date.
To start | Go to the 'Setup' sheet and enter your project details, then open 'Monthly Tracking' and replace the sample rows (highlighted) with your own months and figures.

## Setup
Project Setup
Fill in the yellow cells. These values drive every calculation in the workbook.
Project Name | Riverside Client Portal | Free text label shown on the Dashboard.
Currency | USD | Label only, e.g. USD, EUR, BDT.
Project Start Date | 2026-01-01 | First month of the project.
Planned End Date | 2026-12-31 | Scheduled completion date.
Total Approved Budget (BAC) | 240000 | Budget at Completion - total approved project budget.
Total Contract / Expected Revenue | 300000 | Total revenue you expect to invoice/earn for this project.

## Monthly Tracking
Monthly Budget, Revenue & Earned Value Tracking
Enter your own months and figures in the yellow columns (A-D, F). Everything else is calculated.
Month | Planned % Complete (cumulative) | Actual % Complete (cumulative) | Consumed Budget this month (Actual Cost) | Consumed Budget cumulative (AC) | Revenue Invoiced this month | Revenue cumulative | Planned Value (PV) | Earned Value (EV) | Cost Variance (CV = EV-AC) | Schedule Variance (SV = EV-PV) | CPI (EV/AC) | SPI (EV/PV) | Gross Profit (Revenue - AC) | Profit Margin %
Jan 2026 | 8% | 7% | 18000 | 18000 | 22000 | 22000 | 19200 | 16800 | -1200 | -2400 | 0.93333 | 0.875 | 4000 | 18.18%
Feb 2026 | 17% | 15% | 20000 | 38000 | 25000 | 47000 | 40800 | 36000 | -2000 | -4800 | 0.94737 | 0.88235 | 9000 | 19.15%
Mar 2026 | 25% | 24% | 19500 | 57500 | 24000 | 71000 | 60000 | 57600 | 100 | -2400 | 1.0017 | 0.96 | 13500 | 19.01%
Apr 2026 | 35% | 30% | 21000 | 78500 | 20000 | 91000 | 84000 | 72000 | -6500 | -12000 | 0.9172 | 0.85714 | 12500 | 13.74%
May 2026 | 45% | 40% | 20500 | 99000 | 26000 | 117000 | 108000 | 96000 | -3000 | -12000 | 0.9697 | 0.88889 | 18000 | 15.38%
Jun 2026 | 55% | 52% | 22000 | 121000 | 28000 | 145000 | 132000 | 124800 | 3800 | -7200 | 1.0314 | 0.94545 | 24000 | 16.55%
Latest (Project-to-date) |  |  |  | 121000 |  | 145000 | 132000 | 124800 | 3800 | -7200 | 1.0314 | 0.94545 | 24000 | 16.55%

## Dashboard
Project Dashboard
Project: Riverside Client Portal ¦ As of: Jun 2026 ¦ Currency: USD
Total Budget (BAC) |  | Consumed Budget (AC) |  | Revenue Earned | Gross Profit
240000 |  | 121000 |  | 145000 | 24000
Earned Value (EV) |  | Cost Variance (CV) |  | CPI (Cost Perf. Index) | SPI (Sched. Perf. Index)
124800 |  | 3800 |  | 1.0314 | 0.94545
Month-by-Month Comparison
Month | Planned Value (PV) | Consumed Budget (AC) | Revenue Earned | Earned Value (EV)
Jan 2026 | 19200 | 18000 | 22000 | 16800
Feb 2026 | 40800 | 38000 | 47000 | 36000
Mar 2026 | 60000 | 57500 | 71000 | 57600
Apr 2026 | 84000 | 78500 | 91000 | 72000
May 2026 | 108000 | 99000 | 117000 | 96000
Jun 2026 | 132000 | 121000 | 145000 | 124800